## Introduction
Introduction
Presented here is the Office for Statistics Regulation Rolling Regulatory Work Programme as at 30 December 2020.
This work programme supports our annual 2020/21 Business Plan published on 28 May 2020.
https://osr.statisticsauthority.gov.uk/business-plan/
This work programme will be updated approximately every 6-8 weeks, linked to our internal Programme
Review Board timetable. Any changes to National Statistics designations as a result of our work will be
reflected on the List of National Statistics:
https://osr.statisticsauthority.gov.uk/national-statistics/
Please note that this programme does not include: our casework; any Rapid Reviews linked to the
Covid-19 pandemic; or any blogs. All of that work requires us to be highly responsive and we will take action
and publish as quickly as possible. We maintain a resource headroom as part of our work programme to
ensure we have the required capacity.
The work programme is presented in two parts:
1. Planned
Here we present planned regulatory projects on our work programme. At this time, we are seeking to provide
a six-month horizon. We have two groups of project: (i) Continues as planned: those which are already underway or we can plan with some
certainty; and (ii) Retain flexibility: those we hope to start, resources permitting (OSR and statistics producer).
The second group we will keep under close review within the context of competing demands linked to the COVID-19 pandemic,
and we will prioritise to best serve the public good.
2. Published
Projects will be listed here as projects (or phases of projects) close and we publish our findings, decisions and outcomes.
Listed here are projects/phases that have closed since 1 March 2020. While we do not include Rapid Reviews
in the planned programme we do provide links here to the resulting outcomes.
If you have any questions about the work programme, please contact:
https://osr.statisticsauthority.gov.uk/what-we-do/meet-the-team/
or email:
regulation@statistics.gov.uk

## Planned
Domain | Certainty | Planned Start | Project | Geography | Project Type
Agriculture, Energy and Environment | Continues as planned | October 2020 - March 2021 | Flood and Coastal Erosion Risk Management statistics (Department for Environment, Food and Rural Affairs) | England | Compliance Check
Agriculture, Energy and Environment | Retain flexibility | October 2020 - March 2021 | Natural Capital statistics (Office for National Statistics) | United Kingdom | Compliance Check
Agriculture, Energy and Environment | Retain flexibility | October 2020 - March 2021 | Climate Change statistics: Short focused review leading to OSR Position Statement | United Kingdom | Systemic Review
Business, Trade and International Development | Retain flexibility | Continuing from 2019/20 : Phase 2 | Annual Purchases Survey (Office for National Statistics) | United Kingdom | Assessment
Business, Trade and International Development | Continues as planned | Continuing from 2019/20: Phase 2 | Business Demography (Office for National Statistics) | United Kingdom | Assessment
Business, Trade and International Development | Continues as planned | Continuing from 2019/20: Phase 2 | UK Trade Statistics (Office for National Statistics) | United Kingdom | Assessment
Business, Trade and International Development | Continues as planned | October 2020 - March 2021 | Annual Business Survey (Office for National Statistics) | United Kingdom | Assessment
Business, Trade and International Development | Continues as planned | Continuing from 2019/20 | International Trade in Services (Office for National Statistics) | United Kingdom | Compliance Check
Business, Trade and International Development | Retain flexibility | October 2020 - March 2021 | ONS use of VAT data in Economic statistics (Office for National Statistics) | UK, Scotland, Wales, Northern Ireland and Regions | Compliance Check
Business, Trade and International Development | Retain flexibility | October 2020 - March 2021 | Retail Sales statistics (Office for National Statistics) | United Kingdom | Compliance Check
Children Education and Skills | Continues as planned | October 2020 - March 2021 | Participation Rates in Higher Education (Department for Education) | England | Compliance Check
Children, Education and Skills | Retain flexibility | October 2020 - March 2021 | Graduate Outcomes (Higher Education Statistics Agency) | United Kingdom | Compliance Check
Children, Education and Skills | Retain flexibility | April - September 2020 | Public Value of Post-16 Education and Skills: Phase 2 currently on hold. | United Kingdom | Systemic Review
Crime and Security | Continues as planned | October 2020 - March 2021 | Police Funding statistics (Home Office) | England and Wales | Assessment
Crime and Security | Continues as planned | October 2020 - March 2021 | Scottish Prisons Statistics (Scottish Government) | Scotland | Compliance Check
Crime and Security | Continues as planned | October 2020 - March 2021 | UK Armed Forces Deaths in Service Statistics (Ministry of Defence) | United Kingdom | Compliance Check
Economy | Retain flexibility | October 2020 - March 2021 | Foreign Direct Investment (Office for National Statistics) | United Kingdom | Compliance Check
Economy | Continues as planned | October 2020 - March 2021 | Regional Household Expenditure (Office for National Statistics) | United Kingdom | Compliance Check
Economy | Continues as planned | October 2020 - March 2021 | NI Economic Statistics (Northern Ireland Statistics and Research Agency) | Northern Ireland | Compliance Check
Economy | Continues as planned | Continuing from 2019/20: Phase 2 | HM Revenue and Customs Quality Review | United Kingdom | Special Review
Economy, BTID and Labour Market and Welfare | Continues as planned | October 2020 - March 2021 | Productivity statistics (Office for National Statistics) | United Kingdom | Assessment
Health and Social Care | Continues as planned | Continuing from 2019/20: Phase 2 | Prescription Cost Analysis (NHS Business Services Authority) | England | Assessment
Health and Social Care | Continues as planned | October 2020 - March 2021 | General Pharmaceutical Services statistics (NHS Business Services Authority) | England | Assessment
Health and Social Care | Retain flexibility | October 2020 - March 2021 | NHS Education for Scotland statistics (NHS Education for Scotland) | Scotland | Compliance Check
Health and Social Care | Retain flexibility | Continuing from 2019/20: Phase 2 | Mental Health statistics | England | Systemic Review
Housing, Planning, and Local Services | Retain flexibility | October 2020 - March 2021 | Estimates of Households and Dwellings in Scotland and Household Projections for Scotland (National Records of Scotland) | Scotland | Compliance Check
Housing, Planning, and Local Services | Retain flexibility | October 2020 - March 2021 | Northern Ireland Household Projections (Northern Ireland Statistics and Research Agency) | Northern Ireland | Compliance Check
Housing, Planning, and Local Services | Retain flexibility | October 2020 - March 2021 | Welsh Household Estimates and Welsh Household Projections (Welsh Government) | Wales | Compliance Check
Housing, Planning, and Local Services | Retain flexibility | October 2020 - March 2021 | Fire Incidents statistics and detailed analysis (Home Office) | England | Compliance Check
Housing, Planning, and Local Services | Retain flexibility | October 2020 - March 2021 | Fire and Rescue Performance, Fire Statistics, Deliberate Fires and Grassland Fires (Welsh Government) | Wales | Compliance Check
Labour Market and Welfare | Continues as planned | Continuing from 2019/20: Phase 2 | Quarterly Benefits Summary (Department for Work and Pensions) | Great Britain | Assessment
Labour Market and Welfare | Continues as planned | Continuing from 2019/20: Phase 2 | UK Employment and Jobs statistics (Office for National Statistics), including follow up on Compliance Checks in Scotland, Wales and Northern Ireland | United Kingdom, Scotland, Wales and Northern Ireland | Assessment
Labour Market and Welfare | Continues as planned | October 2020 - March 2021 | Personal Independence Payment statistics (Department for Communities, Northern Ireland) | Northern Ireland | Assessment
Labour Market and Welfare | Retain flexibility | April - September 2020 | Northern Ireland Benefits Statistics Summary (Department for Communities, Northern Ireland) | Northern Ireland | Compliance Check
Labour Market and Welfare | Retain flexibility | October 2020 - March 2021 | Youth Unemployment APS quarterly release (Scottish Government) | Scotland | Compliance Check
Labour Market and Welfare | Continues as planned | October 2020 - March 2021 | Child and Working Tax Credits (HM Revenue and Customs) | United Kingdom | Compliance Check
Labour Market and Welfare | Retain flexibility | October 2020 - March 2021 | Poverty Statistics | United Kingdom | Systemic Review
Population and Society | Continues as planned | Continuing from 2019/20 | 2021 Census (including administrative data sources) (Office for National Statistics, National Records of Scotland, Northern Ireland Statistics and Research Agency) | United Kingdom | Assessment
Population and Society | Retain flexibility | Continuing from 2019/20 | Loneliness statistics | United Kingdom | Systemic Review
Travel Transport and Tourism | Continues as planned | Continuing from 2019/20 : Phase 2 | National Rail Passenger Satisfaction statistics (Transport Focus) | United Kingdom | Assessment
2020 Insight Programme | Continues as planned | April - September 2020 | 2020 Insight: OSR Data Landscape | United Kingdom | Other
2020 Insight Programme | Continues as planned | Continuing from 2019/20 | 2020 Insight: Discovery Phase | United Kingdom | Other
2020 Insight Programme | Continues as planned | Continuing from 2019/20 | 2020 Insight: Delivery Phase - Data Gaps | United Kingdom | Other
Research | Retain flexibility | April - September 2020 | Secondary analysis of OSR regulatory outputs to identify examples of statistics and data use for public good | United Kingdom | Other
Research | Retain flexibility | April - September 2020 | Secondary analysis of National Statistician's Data Ethics Advisory Committee applications to identify examples of statistics and data use for public good | United Kingdom | Other
Research | Continues as planned | Continuing from 2019/20 | Research Programme: Introducing Theory of Change | United Kingdom | Other
Research | Retain flexibility | Continuing from 2019/20 | What do we mean by public good of statistics and what evidence is there already? | United Kingdom | Other
Policy and Standards | Continues as planned | Continuing from 2019/20 | Understanding National Statistics Designation | United Kingdom | Other
Policy and Standards | Retain flexibility | Continuing from 2019/20 | Voluntary Adoption of the Code: We will continue to advocate for voluntary adoption outside the boundaries of official statistics (including new Voluntary Adoption Award) | United Kingdom | Other
Policy and Standards | Retain flexibility | Continuing from 2019/20 | Office for Statistics Regulation response to Public Administration and Constitutional Affairs Committee report “Governance of official statistics: redefining the dual role of the UK Statistics Authority; and re-evaluating the Statistics and Registration Service Act 2007” | United Kingdom | Other
Cross-cutting | Retain flexibility | Continuing from 2019/20 | Framework for Judging Misleadingness | United Kingdom | Other
Cross-cutting | Retain flexibility | April - September 2020 | Reproducible Analytical Pipelines | United Kingdom | Systemic Review
Cross-cutting | Retain flexibility | Continuing from 2019/20 | Public value of statistics on children and younger people: potentially including a focus on child poverty | United Kingdom | Systemic Review
Cross-cutting | Retain flexibility | Continuing from 2019/20 | Statistical Leadership | United Kingdom | Systemic Review
Automation and Technology | Retain flexibility | April - September 2020 | Understand How Statistics Are Used | United Kingdom | Other
Automation and Technology | Retain flexibility | Continuing from 2019/20 | Tracking Official Statistics Publications and Delays | United Kingdom | Other
Automation and Technology | Retain flexibility | Continuing from 2019/20 | Build a Monitoring Dashboard for Regulators | United Kingdom | Other

## Published
Domain | Project | Geography | Project Type | Status | Month | Link to more information
Agriculture, Energy and Environment | Timber Price Indices (Forest Research) | United Kingdom | Compliance Check | Closed | 2020-03-01 | Compliance Check Letter
Agriculture, Energy and Environment | Rural Scotland Key Facts (Scottish Government) | Scotland | Compliance Check | Closed | 2020-04-01 | Compliance Check Letter
Agriculture, Energy and Environment | Interim indicators from the People and Nature Survey for England (Natural England) | England | Rapid Review | Closed | 2020-06-01 | Rapid Review Letter
Agriculture, Energy and Environment | Review of approaches to user engagement across the Department for Environment, Food and Rural Affairs agriculture and environment statistics portfolio | United Kingdom | Systemic Review | Closed | 2020-06-01 | Systemic Review
Agriculture, Energy and Environment | Air Quality Statistics in the UK and Emissions of Air Pollutants in the UK statistics (Department for Environment, Food and Rural Affairs) | United Kingdom | Assessment | Closed | 2020-07-01 | Designation Decision
Agriculture, Energy and Environment | Local Authority Municipal Waste Management statistics for all countries of UK (Department for Environment, Food and Rural Affairs (England); Scottish Environment Protection Agency (Scotland); Welsh Government (Wales); Department for Agriculture, Environment and Rural Affairs (NI)) | England, Scotland, Wales and Northern Ireland | Compliance Checks (x4) | Closed | 2020-10-01 | Compliance Check Letter
Business, Trade and International Development | Business Demography (Office for National Statistics) | United Kingdom | Assessment | Phase 1 closed | 2020-10-01 | Assessment Report
Business, Trade and International Development | Mergers and Acquisitions statistics (Office for National Statistics) | United Kingdom | Compliance Check | Closed | 2020-11-01 | Compliance Check Letter
Children, Education and Skills | Welsh Government Children and staff attendance at local authority settings in Wales during the COVID-19 pandemic (Welsh Government) | Wales | Rapid Review | Closed | 2020-04-01 | Rapid Review Letter
Children, Education and Skills | Attendance in education and early years settings during the COVID-19 pandemic (Department for Education) | England | Rapid Review | Closed | 2020-05-01 | Rapid Review Letter
Children, Education and Skills | Exploring the public value of statistics about post-16 education and skills – UK report | United Kingdom | Systemic Review | Phase 1 Closed | 2020-07-01 | Systemic Review
Crime and Security | PSNI Motoring Offence Statistics (Police Service of Northern Ireland ) | Northern Ireland | Assessment | Closed | 2020-03-01 | Designation Decision
Crime and Security | Proven Re-Offending and Criminal Justice System Statistics (Ministry of Justice) | England and Wales | Compliance Check | Closed | 2020-05-01 | Compliance Check Letter
Crime and Security | Finance and Economics Annual Statistical Bulletin: Trade, Industry and Contracts statistics (Ministry of Defence) | United Kingdom | Compliance Check | Closed | 2020-06-01 | Compliance Check Letter
Crime and Security | Statistics from the Northern Ireland Safe Community Survey (Department of Justice) | Northern Ireland | Compliance Check | Closed | 2020-07-01 | Compliance Check Letter
Crime and Security | Crime statistics: OSR Position Statement | United Kingdom | Position Statement | Closed | 2020-07-01 | Current issues in Crime domain
Crime and Security | Armed Forces Continuous Attitude Survey Statistics (Ministry of Defence) | United Kingdom | Compliance Check | Closed | 2020-08-01 | Compliance Check Letter
Crime and Security | Telephone-Operated Crime Survey for England and Wales (Office for National Statistics) | England and Wales | Rapid Review | Closed | 2020-08-01 | Rapid Review Letter
Crime and Security | Operation of Police Powers under the Terrorism Act 2000 statistics (Home Office) | Great Britiain | Compliance Check | Closed | 2020-10-01 | Compliance Check Letter
Economy | Faster Economic Indicators (Office for National Statistics) | UK | Rapid Review | Closed | 2020-04-01 | Rapid Review Letter
Economy | Strengthening the Quality of HM Revenue and Custom’s Official statistics | United Kingdom | Systemic Review | Phase 1 closed | 2020-04-01 | Systemic Review
Economy | Quality of Survey of Personal Incomes (HM Revenue and Customs) | United Kingdom | Compliance Check | Closed | 2020-10-01 | Compliance Check Letter
Economy | Consumer Price Inflation including Owner-Occupied Housing Costs (CPIH) (Office for National Statistics) | United Kingdom | Follow-Up Review | Closed | 2020-11-01 | Review Letter
Health and Social Care | Recorded Dementia Diagnosis statistics (NHS Digital) | England | Compliance Check | Closed | 2020-03-01 | Compliance Check Letter
Health and Social Care | Mental Health Act statistics (NHS Digital) | England | Compliance Check | Closed | 2020-03-01 | Compliance Check Letter
Health and Social Care | Coronavirus (Covid-19) Infection Survey (Office for National Statistics) | England | Rapid Review | Closed | 2020-05-01 | Rapid Review Letter
Health and Social Care | Rapid Review of NHS England’s statistics on daily Covid-19 deaths in hospitals (NHS England) | England | Rapid Review | Closed | 2020-07-01 | Rapid Review Letter
Health and Social Care | NHS Test and Trace Statistics England (Department of Health and Social Care) | England | Rapid Review | Closed | 2020-07-01 | Rapid Review Letter
Health and Social Care | Mental Health Statistics In England | England | Systemic Review | Phase 1 Closed | 2020-09-01 | Systemic Review
Health and Social Care | Prescription Cost Analysis (NHS Business Services Authority) | England | Assessment | Phase 1 closed | 2020-11-01 | Assessment Report
Health and Social Care | Coronavirus (COVID-19) weekly insights: Key health indicators in England (Office for National Statistics) | England | Rapid Review | Closed | 2020-11-01 | Rapid Review Letter
Health and Social Care | Cancer Survival statistics (Public Health England) | England | Compliance Check | Closed | 2020-12-01 | Compliance Check Letter
Housing, Planning, and Local Services | Northern Ireland Planning statistics (Department for Infrastructure, Northern Ireland) | Northern Ireland | Assessment | Phase 1 closed | 2020-05-01 | Assessment Report
Housing, Planning, and Local Services | Rough Sleeping in Wales (Welsh Government) | Wales | Compliance Check | Closed | 2020-07-01 | Compliance Check Letter
Housing, Planning, and Local Services | Rough Sleeping in England (Ministry of Housing, Communities and Local Government) | England | Compliance Check | Closed | 2020-07-01 | Compliance Check Letter
Housing, Planning, and Local Services | Scottish House Condition Survey (Scottish Government) | Scotland | Compliance Check | Closed | 2020-10-01 | Compliance Check Letter
Housing, Planning, and Local Services | Northern Ireland Planning statistics (Department for Infrastructure, Northern Ireland) | Northern Ireland | Assessment | Closed | 2020-12-01 | Designation letter
Housing, Planning, and Local Services | English Housing Survey (incorporating experimental Leasehold statistics) (Ministry of Housing, Communities and Local Government) | England | Compliance Check | Closed | 2020-12-01 | Compliance Check Letter
Housing, Planning, and Local Services | Land Use Change statistics (Ministry of Housing, Communities and Local Government) | England | Compliance Check | Closed | 2020-12-01 | Compliance Check Letter
Labour Market and Welfare | UK Employment and Jobs statistics (Office for National Statistics), including follow up on Compliance Checks in Scotland, Wales and Northern Ireland | United Kingdom, Scotland, Wales and Northern Ireland | Assessment and Compliance Checks | Phase 1 closed | 2020-03-01 | Assessment Report and Compliance Checks
Labour Market and Welfare | English Indices of Deprivation statistics (Ministry of Housing, Communities and Local Government) | England | Compliance Check | Closed | 2020-07-01 | Compliance Check Letter
Labour Market and Welfare | Scottish Index of Multiple Deprivation (Scottish Government) | Scotland | Compliance Check | Closed | 2020-07-01 | Compliance Check Letter
Labour Market and Welfare | Welsh Index of Multiple Deprivation (Welsh Government) | Wales | Compliance Check | Closed | 2020-07-01 | Compliance Check Letter
Labour Market and Welfare | Coronavirus Job Retention Scheme (CJRS) and Self-Employment Income Support Scheme (SEISS) statistics (HM Revenue and Customs) | United Kingdom | Rapid Review | Closed | 2020-07-01 | Rapid Review Letter
Labour Market and Welfare | Quarterly Benefits Summary (Department for Work and Pensions) | Great Britain | Assessment | Phase 1 closed | 2020-11-01 | Assessment Report
Population and Society | Covid-19 statistics from the Opinions and Lifestyle Survey (Office for National Statistics) | UK | Rapid Review | Closed | 2020-04-01 | Rapid Review Letter
Population and Society | National Survey for Wales (Welsh Government) | Wales | Rapid Review | Closed | 2020-06-01 | Rapid Review Letter
Population and Society | 2021 Census in the UK: Review of Northern Ireland Statistics and Research Agency (NISRA) Response to Preliminary Findings | Northern Ireland | Assessment | Preliminary Phase: Complete | 2020-09-01 | Letter
Population and Society | 2021 Censuses in the UK – Review of Office for National Statistics Response to Preliminary Findings | England and Wales | Assessment | Preliminary Phase: Complete | 2020-09-01 | Letter
Population and Society | 2021 Censuses in the UK – Review of National Records of Scotland (NRS) Response to Preliminary Findings | Scotland | Assessment | Preliminary Phase: Complete | 2020-09-01 | Letter
Population and Society | Internet Use and Access (Office for National Statistics) | Great Britain | Compliance Check | Closed | 2020-10-01 | Compliance Check Letter
Population and Society | National Insurance Number Allocations to Adult Overseas Nationals Entering the UK Statistics (Department for Work and Pensions) | United Kingdom | Assessment | Closed | 2020-11-01 | Designation letter
Travel, Transport and Tourism | Reported Road Casualties in Scotland (Scottish Government) | Scotland | Compliance Check | Closed | 2020-03-01 | Compliance Check Letter
Travel, Transport and Tourism | Police Recorded Road Accident Statistics (Welsh Government) | Wales | Compliance Check | Closed | 2020-03-01 | Compliance Check Letter
Travel, Transport and Tourism | Northern Ireland Road Safety Strategy 2020 (Department for Infrastructure, Northern Ireland) | Northern Ireland | Compliance Check | Closed | 2020-03-01 | Compliance Check Letter
Travel, Transport and Tourism | Police Recorded Injury Road Traffic Collisions and Casualties Northern Ireland statistics (Police Service of Northern Ireland) | Northern Ireland | Compliance Check | Closed | 2020-03-01 | Compliance Check Letter
Travel, Transport and Tourism | Transport Statistics during the COVID-19 pandemic (Department for Transport) | Great Britiain | Rapid Review | Closed | 2020-05-01 | Rapid Review Letter
Travel, Transport and Tourism | Station Usage statistics (Office for Rail Regulation) | Great Britain | Assessment | Phase 1 closed | 2020-11-01 | Assessment Report
Travel, Transport and Tourism | Station Usage statistics (Office for Rail Regulation) | Great Britain | Assessment | Closed | 2020-12-01 | Designation letter
Cross-cutting | Framework for Judging Misleadingness | United Kingdom | Other | Project continues | 2020-05-01 | Think Piece
Cross-cutting | The State of the UK’s Statistical System | United Kingdom | Other | Closed | 2020-07-01 | Report
Research | The Public Good of Statistics: What we know so far | United Kingdom | Other | Ongoing | 2020-12-01 | Research Report