## Introduction
Introduction
Presented here is the Office for Statistics Regulation Rolling Regulatory Work Programme as at 29 July 2021.
This work programme supports our annual 2021/22 Business Plan published on 25 May 2021.
https://osr.statisticsauthority.gov.uk/business-plan/
This work programme is updated approximately every 6-8 weeks, linked to our internal Programme
Review Board timetable. Any changes to National Statistics designations as a result of our work will be
reflected on the List of National Statistics:
https://osr.statisticsauthority.gov.uk/national-statistics/
Please note that this programme does not include our casework or any blogs. Rapid Reviews may also be initiated with immediate effect and so may not feature here.
All of that work requires us to be highly responsive and we will take action and publish as quickly as possible.
We maintain a resource headroom as part of our work programme to ensure we have the required capacity.
The work programme is presented in two parts:
1. Planned
Here we present planned regulatory projects on our work programme. At this time, we are seeking to provide
a six-month horizon. We have two groups of project: (i) Continues as planned: those which are already underway or we can plan with some
certainty; and (ii) Retain flexibility: those we hope to start, resources permitting (OSR and statistics producer).
The second group we will keep under close review within the context of competing demands and we will prioritise to best serve the public good.
2. Published
Projects will be listed here as projects (or phases of projects) close and we publish our findings, decisions and outcomes.
Listed here are projects/phases that have closed since 1 April 2021.
If you have any questions about the work programme, please contact:
https://osr.statisticsauthority.gov.uk/what-we-do/meet-the-team/
or email:
regulation@statistics.gov.uk

## Planned
Domain | Certainty | Planned start | Project | Geography | Project Type
Agriculture Energy and Environment | Continue as planned | Continuing from 2020/21 | Climate Change statistics | United Kingdom | Systemic Review
Agriculture Energy and Environment (cross-cutting with Health and Social Care, Labour Market and Welfare and Economy) | Continue as planned | April - September 2021 | Food statistics | United Kingdom | Systemic Review; Compliance Checks
Agriculture Energy and Environment | Continue as planned | Continuing from 2020/21 | UK Natural Capital Accounts (Office for National Statistics) | United Kingdom | Compliance Check
Agriculture Energy and Environment | Continue as planned | April - September 2021 | Funding for flood and coastal erosion risk management in England | England | Compliance Check
Crime and Security | Retain flexibility | April - September 2021 | Telephone Crime Survey for England and Wales (Office for National Statistics) | England and Wales | Compliance Check
Crime and Security | Continue as planned | April - September 2021 | UK Armed Forces Mental Health statistics (Ministry of Defence) | United Kingdom | Compliance Check
Crime and Security | Continue as planned | April - September 2021 | Criminal Proceedings in Scotland statistics (Scottish Government) | Scotland | Compliance Check
Crime and Security (cross-cutting with Housing, Planning and Local Services) | Continue as planned | April - September 2021 | Mortgage and landlord possession statistics (Ministry of Justice) | England and Wales | Compliance Check
Crime and Security, Data and Automation | Continue as planned | April - September 2021 | New Estimates of Knife Crime (Office for National Statistics, Home Office) | England and Wales | Compliance Check
Economy and Business Trade and International Development | Continue as planned | Continuing from 2020/21 | Annual Purchases Survey (Office for National Statistics) | United Kingdom | Assessment
Economy and Business Trade and International Development | Continue as planned | Continuing from 2020/21 | Annual Business Survey (Office for National Statistics) | United Kingdom | Assessment
Economy and Business Trade and International Development | Continue as planned | Continuing from 2020/21 | Productivity statistics (Office for National Statistics) | United Kingdom | Assessment: Phase 2
Economy and Business Trade and International Development | Continue as planned | Continuing from 2020/21 | UK Trade statistics (Office for National Statistics) | United Kingdom | Assessment: Phase 2
Economy and Business Trade and International Development | Continue as planned | Continuing from 2020/21 | Business Demography (Office for National Statistics) | United Kingdom | Assessment: Phase 2
Economy and Business Trade and International Development | Continue as planned | April - September 2021 | Broad Economy, Sales and Exports statistics (Northern Ireland Statistics and Research Agency) | Northern Ireland | Assessment
Economy and Business Trade and International Development | Continue as planned | April - September 2021 | Public Service Productivity (Office for National Statistics) | United Kingdom | Compliance Check
Economy and Business Trade and International Development | Continue as planned | April - September 2021 | Inheritance Tax (HM Revenue and Customs) | United Kingdom | Compliance Check
Economy and Business Trade and International Development | Continue as planned | April - September 2021 | Review of ONS's arrangements for sector classifications | United Kingdom | Systemic Review
Economy and Business Trade and International Development | Retain flexibility | October 2021 - March 2022 | Country and Regional Public Sector Finance statistics (Office for National Statistics, HM Treasury) | United Kingdom | Assessment
Economy and Business Trade and International Development | Retain flexibility | October 2021 - March 2022 | Regional GDP estimates (Office for National Statistics) | United Kingdom | Assessment
Health and Social Care | Continue as planned | Continuing from 2020/21 | General Pharmaceutical Services (NHS Business Services Authority) | England | Assessment: Phase 2
Health and Social Care | Continue as planned | Continuing from 2020/21 | Mental Health statistics Northern Ireland | Northern Ireland | Systemic review
Health and Social Care | Continue as planned | April - September 2021 | Northern Ireland Outpatient Waiting Times (Department of Health, Northern Ireland) | Northern Ireland | Compliance check
Health and Social Care | Continue as planned | April - September 2021 | Care Quality Commission Patient Experience Survey statistics (Care Quality Commission) | England | Compliance checks
Health and Social Care | Continue as planned | April - September 2021 | COVID-19 Lessons Learnt Review | United Kingdom | Other: Review
Health and Social Care | Retain flexibility | April - September 2021 | Adult Social Care in Great Britain: Follow Up Review | Great Britain | Systemic Review
Housing Planning and Local Services | Continue as planned | April - September 2021 | Statutory Homelessness statistics in England (Experimental) (Ministry of Housing, Communities and Local Government) | England | Assessment
Housing, Planning, and Local Services | Continue as planned | Continuing from 2020/21 | Estimates of Households and Dwellings in Scotland and Household Projections for Scotland (National Records of Scotland) | Scotland | Compliance Check
Housing, Planning, and Local Services | Continue as planned | Continuing from 2020/21 | Northern Ireland Household Projections (Northern Ireland Statistics and Research Agency) | Northern Ireland | Compliance Check
Housing, Planning, and Local Services | Continue as planned | Continuing from 2020/21 | Welsh Household Estimates and Welsh Household Projections (Welsh Government) | Wales | Compliance Check
Housing Planning and Local Services | Continue as planned | April - September 2021 | Local Authority Green Belt Statistics for England (Ministry of Housing, Communities and Local Government) | England | Compliance Check
Labour Market and Welfare | Continue as planned | Continuing from 2020/21 | Personal Independence Payment statistics (Department for Communities, Northern Ireland) | Northern Ireland | Assessment: Phase 2
Labour Market and Welfare | Continue as planned | Continuing from 2020/21 | Employment and Jobs Statistics (Office for National Statistics) | United Kingdom | Assessment: Phase 2
Labour Market and Welfare | Continue as planned | Continuing from 2020/21 | Income-based Poverty statistics (Department for Work and Pensions, Office for National Statistics) | United Kingdom | Systemic Review: Phase 2
Labour Market and Welfare | Continue as planned | Continuing from 2020/21 | The Living Costs and Food Survey | United Kingdom | Assessment:Phase 2
Labour Market and Welfare | Retain flexibility | April - September 2021 | Income Estimates for Small Areas, England and Wales (Office for National Statistics) | England and Wales | Compliance Check
Population and Society | Continue as planned | Continuing from 2020/21 | 2021 Census (including administrative data sources) (Office for National Statistics, National Records of Scotland, Northern Ireland Statistics and Research Agency) | England, Wales, Scotland, Northern Ireland | Assessment
Population and Society | Continue as planned | Continuing from 2020/21 | Loneliness data and statistics | United Kingdom | Systemic Review
Population and Society | Continue as planned | April - September 2021 | International Migration estimates (Office for National Statistics) | United Kingdom | Other: Watching Brief
Population and Society | Continue as planned | April - September 2021 | Gender identity and Scottish Household Survey (Scottish Government) | Scotland | Compliance Check
Population and Society, Crime and Security | Retain flexibility | April - September 2021 | Coroners statistics (Ministry of Justice) | England and Wales | Compliance Check
Travel Transport and Tourism | Continue as planned | Continuing from 2020/21 | National Rail Passenger Survey (Transport Focus) | Great Britain | Assessment: Phase 2
Travel Transport and Tourism | Retain flexibility | April - September 2021 | Accessibility of Transport Networks | United Kingdom | Systemic Review; Compliance Checks
Cross-cutting | Continue as planned | Continuing from 2020/21 | Children and Young People Review – the Three Vs | United Kingdom | Systemic Review
Cross-cutting | Continue as planned | Continuing from 2020/21 | Statistical Leadership | United Kingdom | Systemic Review
Cross-cutting | Continue as planned | April - September 2021 | State of the Statistical System | United Kingdom | Systemic Review: Phase 2
Research | Continue as planned | Continuing from 2020/21 | OSR Synthesis of Existing Regulatory Work | United Kingdom | Research
Research | Continue as planned | April - September 2021 | Primary Research with the Public to Understand Definitions of Public Good | United Kingdom | Research
Data and Automation | Continue as planned | Continuing from 2020/21 | Statistical models for awarding exam grades - follow up | United Kingdom | Other: Review
Data and Automation | Continue as planned | Continuing from 2020/21 | Reproducible Analytical Pipelines (RAP) Review | United Kingdom | Data and Automation
Data and Automation | Continue as planned | Continuing from 2020/21 | Guidance on Code and Statistical Models | United Kingdom | Data and Automation
Data and Automation | Continue as planned | April - September 2021 | Automated scraping of Hansard and insight analysis | United Kingdom | Data and Automation
Data and Automation | Continue as planned | April - September 2021 | Analysing Google Trends to Understand Data Gaps | United Kingdom | Data and Automation
Data and Automation | Continue as planned | April - September 2021 | Building a Generic Topic Analysis Tool | United Kingdom | Data and Automation
Insight | Retain flexibility | April - September 2021 | Insight: How producers describe uncertainty in the statistics they publish | United Kingdom | Insight
Insight | Retain flexibility | April - September 2021 | Insight: The role of statistics in evaluating policy impacts | United Kingdom | Insight
Policy and Standards | Continue as planned | Continuing from 2020/21 | National Statistics Review | United Kingdom | Policy and Standards
Policy and Standards | Continue as planned | Continuing from 2020/21 | Advocating the Code Pillars Beyond Official Statistics: Voluntary Application | United Kingdom | Policy and Standards
Policy and Standards | Retain flexibility | Continuing from 2020/21 | Developing Online Learning and Guidance For Different Audiences | United Kingdom | Policy and Standards
Policy and Standards | Continue as planned | April - September 2021 | Review the Relevance of the Code: 9.30am Release | United Kingdom | Policy and Standards
Regulation Support | Continue as planned | Continuing from 2020/21 | OSR Process Improvement | United Kingdom | Corporate
Regulation Support (cross-cutting with Data and Automation and Insight) | Continue as planned | Continuing from 2020/21 | Building OSR Intelligence Capacity | United Kingdom | Corporate

## Published
Domain | Project | Geography | Project Type | Status | Month | Link to more information
Children Education and Skills | Programme for International Student Assessment (PISA) (Department for Education, Welsh Government, Scottish Government, Department of Education Northern Ireland) | England, Wales, Scotland and Northern Ireland | Compliance Checks | Closed | 2021-05-01 | Compliance Check Letters
Crime and Security | Police Funding statistics (Home Office) | England and Wales | Assessment | Phase 1 Closed | 2021-06-01 | Assessment Report
Crime and Security | Police Funding statistics (Home Office) | England and Wales | Assessment | Closed | 2021-07-01 | Confirmation Letter
Crime and Security | Criminal Proceedings in Scotland statistics (Scottish Government) | Scotland | Compliance Check | Closed | 2021-07-01 | Compliance Check Letter
Crime and Security (cross-cutting with Labour Market and Welfare) | Ministry of Defence Regional Expenditure with UK Industry and Supported Employment (Ministry of Defence) | United Kingdom | Compliance Check | Closed | 2021-07-01 | Compliance Check Letter
Economy and Business Trade and International Development | Foreign Direct Investment statistics (Office for National Statistics) and Inward Investment statistics (Department for International Trade) | United Kingdom | Compliance Check | Closed | 2021-04-01 | Compliance Check Letter
Economy and Business Trade and International Development | Productivity statistics (Office for National Statistics) | United Kingdom | Assessment | Phase 1 Closed | 2021-05-01 | Assessment Report
Health and Social Care | COVID-19 Vaccinations statistics (NHS England) | England | Rapid Review | Closed | 2021-04-01 | Rapid Review Letter
Health and Social Care | Weekly Statistics for Rapid Asymptomatic Testing in England (Department of Health and Social Care) | England | Rapid Review | Closed | 2021-04-01 | Rapid Review Letter
Health and Social Care | Prescription Cost Analysis (NHS Business Services Authority) | England | Assessment | Closed | 2021-05-01 | Confirmation Letter
Health and Social Care | General Pharmaceutical Services (NHS Business Services Authority) | England | Assessment | Phase 1 Closed | 2021-07-01 | Assessment Report
Housing, Planning, and Local Services | Fire Incidents statistics and detailed analysis (Home Office) | England | Compliance Check | Closed | 2021-05-01 | Compliance Check
Housing, Planning, and Local Services | Fire and Rescue Incident Statistics, Grassland Fires, Deliberate Fires, and Fire and Rescue Authority Performance (Welsh Government) | Wales | Compliance Check | Closed | 2021-06-01 | Compliance Check Letter
Housing Planning and Local Services | Local Authority Revenue Expenditure and Financing Budget statistics (Ministry of Housing, Communities and Local Government) | England | Compliance Check | Closed | 2021-06-01 | Letter restoring NS designation
Housing Planning and Local Services | Scottish Vacant and Derelict Land survey (Scottish Government) | Scotland | Compliance Check | Closed | 2021-07-01 | Compliance Check Letter
Labour Market and Welfare | Personal Independence Payment statistics (Department for Communities, Northern Ireland) | Northern Ireland | Assessment | Phase 1 Closed | 2021-05-01 | Assessment Report
Labour Market and Welfare | Labour Market statistics for Young People (Scottish Government) | Scotland | Compliance Check | Closed | 2021-05-01 | Compliance Check Letter
Labour Market and Welfare | Income-based Poverty statistics (Department for Work and Pensions, Office for National Statistics) | United Kingdom | Systemic Review | Phase 1 Closed | 2021-05-01 | Published Report
Labour Market and Welfare | The Living Costs and Food Survey (Office for National Statistics) | United Kingdom | Assessment | Phase 1 Closed | 2021-07-01 | Assessment Report
Labour Market and Welfare | Quarterly Benefits Summary (Department for Work and Pensions) | Great Britain | Assessment | Closed | 2021-07-01 | Confirmation letter
Population and Society | Review of Population Estimates and Projections Produced by the Office for National Statistics | United Kingdom | Review | Closed | 2021-05-01 | Published Report
Cross-cutting | Misleadingness: Paper 2 | United Kingdom | Other | Ongoing | 2021-05-01 | Paper
Cross-cutting | State of the Statistical System | United Kingdom | Systemic Review | Phase 1 Closed | 2021-07-01 | Published Report
Policy and Standards | National Statistics Review | United Kingdom | Policy and Standards | Ongoing | 2021-06-01 | Phase 3 Report
Research | Defining the Public Good in Applications to Access Public Data | United Kingdom | Research | Ongoing | 2021-05-01 | Research Report